PolicyHub

Sprint Breakdown — Stories & Acceptance Criteria

Version 1.0  ·  March 2026  ·  Confidential

This document breaks the five development milestones into ten sprints (10 working days each). Each sprint contains user stories with acceptance criteria, size estimates, and dependencies.

Story point scale: XS=1, S=2, M=3, L=5, XL=8  ·  Sprint capacity: ~30–35 points

| Milestone | Sprint(s) | Days | Theme | Gate |
| --- | --- | --- | --- | --- |
| M1: Auth + Editor | 1–2 | Days 1–20 | A logged-in policy author can create a policy, write content in the WYSIWYG editor, and have that content committed to a… | Usability test with 3 policy authors |
| M2: Review workflow | 3–4 | Days 1–45 | A policy author can submit a draft for review. A reviewer can read a diff, leave comments, and approve or request change… | Usability test with 3 reviewers |
| M3: Publishing pipeline & version history | 5 | Days 1–70 | Approved policies are published: Markdown is rendered to HTML and PDF, committed to main, and a permanent version snapsh… | Internal walkthrough with the full approval chain |
| M4: Reader portal & search | 6 | Days 1–95 | All staff can browse and search published policies. Access is role-filtered. Typesense full-text search is live. Admin c… | Broad staff pilot (all staff with policy library access) |
| M5: AI features | 7 | Days 1–130 | The policy bot answers questions from published policies with citations. AI change summaries are generated during submis… | Red team evaluation (internal policy team stress-tests the bot for hallucination and RBAC leakage) + pilot with 10 staff |

M1  Auth + Editor  ·  Day 20

Goal: A logged-in policy author can create a policy, write content in the WYSIWYG editor, and have that content committed to a GitLab branch.

Test gate: Usability test with 3 policy authors. Success criterion: author completes a draft from blank to saved without assistance.

Sprint 1  ·  Days 1–10  ·  Project foundations & SSO auth  ·  28 pts

Objective: Running application with working Entra SSO login. A developer can clone the repo, run docker-compose up, and land on a dashboard behind authentication.

10 stories  ·  28 story points

| S1-01 | Docker Compose local environment | M (3) |
| --- | --- | --- |
| User story | As a developer, I want a single docker-compose up command that starts PostgreSQL, Valkey, and a stub Typesense instance — so that I can run the full application stack locally without manual service installation |  |
| Acceptance criteria | - docker-compose up starts PostgreSQL 16, Valkey 7, and Typesense 28 containers - A .env.example file documents every required environment variable with description and example value - node ace migration:run runs without errors against the Dockerised Postgres instance - README.md contains a working "Getting started in 5 minutes" section - Health-check endpoints confirm each service is running before the app starts |  |

| S1-02 | AdonisJS v7 project scaffold | M (3) |
| --- | --- | --- |
| User story | As a developer, I want a fully scaffolded AdonisJS v7 project with all required first-party packages installed and configured — so that the team starts from a consistent, pre-wired foundation rather than assembling packages independently |  |
| Acceptance criteria | - Project created with: npm create adonisjs@latest policy-platform -- --kit=react - All first-party packages added in correct order: bouncer, mail, drive, redis (Valkey), queue, limiter - config/database.ts points to PostgreSQL (not default SQLite) - All 22 path aliases defined in package.json imports map (see project-structure doc) - node ace serve --hmr starts without errors - node ace build completes without errors |  |
|  | Depends on | S1-01 |  |

| S1-03 | Database migrations 001–010 | M (3) |
| --- | --- | --- |
| User story | As a developer, I want the first ten database migrations (users through workflow_instances) to run cleanly — so that the core user, role, and policy tables exist before any application logic is written |  |
| Acceptance criteria | - Migrations 001–010 run in order without errors: users, roles, user_roles, idp_group_role_mappings, audience_groups, user_audience_groups, categories, policies, policy_versions, workflow_instances - node ace migration:rollback reverses all ten migrations cleanly - Each migration file has a descriptive comment block explaining the table's purpose - Lucid models auto-generated for each table after migration:run - Database ERD comment in the migration folder links to the schema-api doc |  |
|  | Depends on | S1-02 |  |

| S1-04 | Entra SSO login via OIDC | L (5) |
| --- | --- | --- |
| User story | As a policy author, I want to click "Sign in with your organisation account" and be redirected to Entra for authentication — so that I use my existing corporate credentials without a separate PolicyHub password |  |
| Acceptance criteria | - GET /auth/sso/redirect redirects to the Entra authorisation endpoint - GET /auth/sso/callback exchanges the code, fetches the token, and creates or updates the user record - User record stores idp_subject (Entra oid claim) and idp_provider = "entra" - Successful login redirects to /dashboard - A failed or cancelled OIDC flow redirects to the login page with a human-readable error message - Session is established with a secure, HttpOnly, SameSite=Lax cookie |  |
|  | Depends on | S1-03 |  |

| S1-05 | IdP group → role mapping on login | M (3) |
| --- | --- | --- |
| User story | As a system, I want to assign application roles to a user based on their Entra group memberships at login time — so that role changes in Entra take effect the next time a user signs in without manual role management in PolicyHub |  |
| Acceptance criteria | - The OIDC callback reads the groups claim from the ID token (claim name configured via IDP_GROUPS_CLAIM env var) - For each group ID, the idp_group_role_mappings table is queried and matching roles are upserted to user_roles - Roles not present in the current groups claim are removed from user_roles on each login - A user with no mapped groups receives no roles and sees an "access pending" screen - Mapping logic is covered by unit tests using fixture group/role data (no live Entra required) |  |
|  | Depends on | S1-04 |  |

| S1-06 | Auth middleware & route protection | S (2) |
| --- | --- | --- |
| User story | As a developer, I want all application routes (except /auth/*) to require an authenticated session — so that unauthenticated requests are redirected to login and cannot access any application data |  |
| Acceptance criteria | - Unauthenticated GET /dashboard redirects to /auth/login - Unauthenticated API requests (Accept: application/json) receive 401 JSON, not a redirect - Auth middleware attaches the authenticated user to ctx.auth.user on every protected request - POST /auth/logout destroys the session and redirects to /auth/login - Local auth (POST /auth/local/login) is only registered when LOCAL_AUTH_ENABLED=true env var is set - loginAs() works in Japa test environment for all auth-gated route tests |  |
|  | Depends on | S1-05 |  |

| S1-07 | Dashboard shell with empty state | S (2) |
| --- | --- | --- |
| User story | As a policy author, I want to see a dashboard after logging in that shows my name and an empty state message when I have no policies — so that I can confirm login worked and know how to create my first policy |  |
| Acceptance criteria | - GET /dashboard renders the Dashboard Inertia page with the authenticated user's name in the sidebar - Empty state shows "No policies yet — create your first" with a prominent "+ New Policy" button - Sidebar navigation renders all items from the spec (Dashboard, My Policies, Review Queue, Policy Library) - Active nav item is highlighted correctly per route - Page title is "Dashboard — PolicyHub" - Passes Lighthouse accessibility score ≥ 90 |  |
|  | Depends on | S1-06 |  |

| S1-08 | Feature flag: local auth for testing | S (2) |
| --- | --- | --- |
| User story | As a developer, I want a LOCAL_AUTH_ENABLED flag that enables a username/password login form backed by the users table — so that automated tests and staging environments can authenticate without a live Entra connection |  |
| Acceptance criteria | - When LOCAL_AUTH_ENABLED=false (default), POST /auth/local/login returns 404 - When LOCAL_AUTH_ENABLED=true, POST /auth/local/login accepts email + password and creates a session - Local users are created via node ace db:seed and are distinguishable by idp_provider = "local" - Local auth is explicitly documented in README as development-only — not for production use - CI pipeline sets LOCAL_AUTH_ENABLED=true; production deployment docs warn against it |  |
|  | Depends on | S1-06 |  |

| S1-09 | GitLab service account integration | M (3) |
| --- | --- | --- |
| User story | As a developer, I want a GitLab service configured with a working API token and content repository — so that the application can perform git operations (create branch, commit, open MR) via the GitLab REST API |  |
| Acceptance criteria | - GitLab service reads GITLAB_BASE_URL, GITLAB_TOKEN, GITLAB_PROJECT_ID from env - GitLabService.testConnection() method returns true when credentials are valid - A node ace gitlab:setup command documents the manual setup steps for the content repo (branch protection, webhook) - GitLabService is registered as a singleton in the IoC container - All GitLab API errors are caught, logged, and wrapped in typed application errors (not raw Axios errors) - Rate limit responses (429) trigger exponential backoff via the queue layer |  |
|  | Depends on | S1-02 |  |

| S1-10 | Audit log middleware | S (2) |
| --- | --- | --- |
| User story | As a compliance officer, I want every significant user action to be recorded in an immutable audit log — so that I can produce a complete activity trail for any policy for compliance purposes |  |
| Acceptance criteria | - audit_logs table exists (migration 022 from schema doc) - AuditLogService.record(actor, action, resource, metadata) writes to the table - Login, logout, and all workflow state transitions are automatically logged - Audit log entries are append-only — no UPDATE or DELETE permissions on the table in the service - node ace audit:export --policy=<id> outputs a CSV of all events for a given policy |  |
|  | Depends on | S1-03 |  |

Sprint 2  ·  Days 11–20  ·  Policy creation & TipTap editor  ·  29 pts

Objective: An author can create a policy, write content in the WYSIWYG editor, and have that content committed to a GitLab branch. The Milestone 1 test gate can be run.

10 stories  ·  29 story points

| S2-01 | New policy wizard — step 1: basic details | S (2) |
| --- | --- | --- |
| User story | As a policy author, I want a guided wizard where I enter a policy title, select a category, and add a description — so that the policy is correctly categorised before I start writing |  |
| Acceptance criteria | - GET /policies/new renders the 3-step wizard, step 1 active - Title field: required, 5–200 characters, trimmed - Category field: required, populated from categories table - Description: optional, max 500 characters - VineJS validation returns field-level errors displayed inline (not as a toast) - "Next" is disabled until title and category are valid |  |
|  | Depends on | S1-07 |  |

| S2-02 | New policy wizard — step 2: metadata | M (3) |
| --- | --- | --- |
| User story | As a policy author, I want to set policy owner, audience groups, review date, and related policies in the wizard — so that the publishing pipeline has all the metadata it needs to generate the boilerplate |  |
| Acceptance criteria | - Owner: free-text or user picker, required - Audience groups: multi-select from audience_groups table, at least one required - Review date: date picker, must be in the future - Related policies: optional multi-select from existing published policies - All metadata is stored in the policies table (not inside the Markdown) - "Back" returns to step 1 with values preserved |  |
|  | Depends on | S2-01 |  |

| S2-03 | New policy wizard — step 3: template selection | M (3) |
| --- | --- | --- |
| User story | As a policy author, I want to choose a policy template (or blank) before the editor opens — so that my policy starts with the correct section structure for its type |  |
| Acceptance criteria | - At least two templates available: "Standard Policy" (Purpose/Scope/Policy/Definitions/Related) and "Blank" - Templates are stored as Markdown files in the application (not in GitLab) - Selecting a template shows a preview of the section headings - Submitting the wizard creates the policy record (status: draft) and redirects to the editor - Creating a policy fires a GitLab branch creation: content/policy-<slug> off main |  |
|  | Depends on | S2-02, S1-09 |  |

| S2-04 | TipTap WYSIWYG editor — core | L (5) |
| --- | --- | --- |
| User story | As a policy author, I want a rich-text editor that supports headings (H1–H3), bold, italic, bullet lists, numbered lists, and tables — so that I can write a complete, formatted policy document without touching Markdown |  |
| Acceptance criteria | - TipTap editor renders in the editor page with all extensions from the spec loaded - Toolbar buttons for: H1, H2, H3, bold, italic, bullet list, numbered list, table insert - Editor content round-trips to Markdown without formatting loss (test with a document containing all supported elements) - Paste from Microsoft Word strips unsupported formatting and preserves text and basic structure - Editor is accessible: all toolbar actions reachable by keyboard |  |
|  | Depends on | S2-03 |  |

| S2-05 | Markdown source toggle | S (2) |
| --- | --- | --- |
| User story | As a policy author, I want to toggle between the WYSIWYG view and raw Markdown source — so that I can make precise edits when the WYSIWYG editor does not produce the output I need |  |
| Acceptance criteria | - An "MD" button in the toolbar switches the editor to a plain textarea showing raw Markdown - Switching back to WYSIWYG re-parses the Markdown and renders the editor - If the Markdown contains syntax errors, an inline warning is shown and the toggle is blocked until fixed - The source mode toggle is in a distinct visual state to avoid accidental edits in the wrong mode |  |
|  | Depends on | S2-04 |  |

| S2-06 | Auto-save and manual save to GitLab | L (5) |
| --- | --- | --- |
| User story | As a policy author, I want my edits to be saved automatically every 30 seconds and on explicit save (Ctrl+S) — so that I never lose work due to a browser crash or accidental navigation |  |
| Acceptance criteria | - Auto-save fires 30 seconds after the last keystroke (debounced, not on a fixed timer) - Each save commits the Markdown file to the policy's GitLab branch with message: "Auto-save: <timestamp>" - Explicit save (Ctrl+S or Save button) commits with message: "Manual save: <timestamp>" - Save status shown in the topbar: "Saving…", "Saved 2 min ago", "Save failed — retry" - If GitLab is unreachable, content is buffered in Valkey and retried via the queue - A conflict warning appears if another user has committed to the same branch since last load |  |
|  | Depends on | S2-04, S1-09 |  |

| S2-07 | Policy list on dashboard | M (3) |
| --- | --- | --- |
| User story | As a policy author, I want to see all my policies in a table on the dashboard, with their status and last-updated date — so that I can navigate to any of my policies without searching |  |
| Acceptance criteria | - Dashboard shows a "My Policies" table with columns: Title, Category, Status, Updated, Actions - Status badges match spec colours: Draft (grey), In review (blue), Changes requested (amber), Published (green) - Edit action appears for Draft and Changes-requested policies; View for all others - Table is paginated at 20 rows; client-side sort by Title and Updated - Empty state shown when the user has no policies - "+ New Policy" button in topbar is always visible |  |
|  | Depends on | S2-03, S1-07 |  |

| S2-08 | Metadata strip on editor page | S (2) |
| --- | --- | --- |
| User story | As a policy author, I want to see the policy's category, audience, review date, and related policies while editing — so that I have context without having to leave the editor to check |  |
| Acceptance criteria | - A read-only metadata strip appears between the topbar and the editor toolbar - "Edit metadata" button opens a slide-over panel (not a full-page navigation) allowing in-place edits to metadata fields - Changes to metadata in the slide-over are saved separately from document content (PATCH /api/v1/policies/:id) - Related policies shown as tag chips; clicking one opens the policy in a new tab |  |
|  | Depends on | S2-04 |  |

| S2-09 | Policy edit routing and access control | S (2) |
| --- | --- | --- |
| User story | As a system, I want the editor to be accessible only to the policy's author and users with policy:admin role — so that other users cannot modify a policy they do not own |  |
| Acceptance criteria | - GET /policies/:id/edit returns 403 if the requesting user is not the policy owner or policy:admin - Policies in "In review" or later states cannot be edited — the edit route returns a redirect to the view page with a notice - Bouncer policy (PolicyPolicy) covers: view, edit, submit, withdraw - All Bouncer checks are covered by unit tests using the loginAs() helper |  |
|  | Depends on | S2-04, S1-06 |  |

| S2-10 | Milestone 1 test gate preparation | S (2) |
| --- | --- | --- |
| User story | As a developer, I want a seed script that creates realistic test data for the M1 usability test — so that the usability test participants have a realistic environment to work in |  |
| Acceptance criteria | - node ace db:seed --seeder=UsabilityM1Seeder creates: 3 test users with policy:author role, 4 categories, 2 draft policies with content - Seeder outputs test user credentials to the console (only when LOCAL_AUTH_ENABLED=true) - All 10 Sprint 1+2 stories have end-to-end test coverage using Playwright - CI pipeline passes before the usability test is scheduled |  |
|  | Depends on | S2-07, S1-08 |  |

M2  Review workflow  ·  Day 45

Goal: A policy author can submit a draft for review. A reviewer can read a diff, leave comments, and approve or request changes. The basic approval loop is complete.

Test gate: Usability test with 3 reviewers. Success criterion: reviewer can evaluate a diff and make a decision without assistance. Key risk: diff readability.

Sprint 3  ·  Days 21–30  ·  Submit for review & review queue  ·  31 pts

Objective: An author can submit a policy for review. The assigned reviewer sees it in their queue.

10 stories  ·  31 story points

| S3-01 | Database migrations 011–016 | S (2) |
| --- | --- | --- |
| User story | As a developer, I want migrations for workflow_approvals, comments, notifications, and audit log extensions — so that the workflow and communication tables exist before workflow logic is written |  |
| Acceptance criteria | - Migrations 011–016 run cleanly: workflow_approvals, comments, notification_preferences, notifications, policy_related_policies, audit_logs - Migration 012 includes the deferred ALTER TABLE to resolve the policies ↔ policy_versions circular FK (per schema doc) - Rollback works cleanly for all six |  |
|  | Depends on | S1-03 |  |

| S3-02 | AI change summary generation | L (5) |
| --- | --- | --- |
| User story | As a policy author, I want an AI-generated plain-English summary of my changes to appear when I click "Submit for review" — so that I can verify the summary accurately describes what changed before reviewers see it |  |
| Acceptance criteria | - On clicking "Submit for review", the application fetches the git diff between the current branch and main - The diff is sent to Claude (claude-sonnet-4-6) with a strict prompt: "Summarise the changes to this policy document in 2–3 sentences of plain English. Focus on what changed, not formatting." - The summary is displayed on the Submit for Review screen for the author to verify - If the author edits the summary, their version is used (stored on the workflow_instance) - If Claude API is unavailable, the field shows "Summary unavailable — please write one" with a text area - Generation is triggered once on page load, not on every render |  |
|  | Depends on | S2-06, S3-01 |  |

| S3-03 | Change magnitude calculation | S (2) |
| --- | --- | --- |
| User story | As a system, I want to calculate a change magnitude score from the git diff when a policy is submitted — so that reviewers and approvers have a quick sense of how substantial the changes are before reading the diff |  |
| Acceptance criteria | - Magnitude is calculated as: (lines added + lines removed) / total lines in document, capped at 1.0 - Score is stored on the workflow_instance as change_magnitude (decimal) - Score < 0.15: "Low", 0.15–0.40: "Medium", > 0.40: "High" - High magnitude requires an author-provided justification field (min 50 chars) before submission proceeds - Score and label are shown as a visual bar on the Submit screen and on the review screen header |  |
|  | Depends on | S3-01 |  |

| S3-04 | Reviewer and approver assignment | M (3) |
| --- | --- | --- |
| User story | As a policy author, I want to assign a reviewer and L1 approver when submitting my policy — so that the right people are notified and the workflow is directed correctly |  |
| Acceptance criteria | - Reviewer select: users with policy:reviewer role, searchable by name - L1 Approver select: users with policy:approver:l1 role, searchable by name - L2 Approver: pre-populated from category defaults (categories.default_l2_approver_id), shown read-only - If no category default is set, L2 Approver is a required free select from policy:approver:l2 users - All three assignments are stored on workflow_instances |  |
|  | Depends on | S3-01 |  |

| S3-05 | Submit workflow action — GitLab MR creation | L (5) |
| --- | --- | --- |
| User story | As a policy author, I want to click "Submit for review" and have the policy enter the review state with a GitLab MR opened — so that the diff is captured in git and the review workflow begins |  |
| Acceptance criteria | - POST /api/v1/policies/:id/workflow/submit transitions status to "in_review" - A GitLab MR is opened: source = content/policy-<slug>, target = main, title = "Review: <policy title>" - MR description contains the AI change summary and a link back to the PolicyHub review page - workflow_instances row is created with state = "review", reviewer_id, l1_approver_id, l2_approver_id - Transition is rejected if policy is not in "draft" state - Action is atomic: if GitLab MR creation fails, the workflow_instance state is not persisted |  |
|  | Depends on | S3-02, S3-03, S3-04 |  |

| S3-06 | Review notification email | M (3) |
| --- | --- | --- |
| User story | As a reviewer, I want to receive an email when a policy is submitted for my review — so that I know a policy needs my attention without logging in to check |  |
| Acceptance criteria | - On submit, a ReviewRequestedMail is queued via @adonisjs/queue - Email includes: policy title, author name, AI change summary, direct link to the review screen - Mail is sent from a configured FROM address (MAIL_FROM env var) - If the reviewer has muted notifications for this policy, no email is sent - Mailer is configured for SMTP in production, in-memory log driver in test/dev - Email delivery failure is logged to audit_logs but does not block the workflow transition |  |
|  | Depends on | S3-05 |  |

| S3-07 | Review queue screen | M (3) |
| --- | --- | --- |
| User story | As a reviewer, I want to see a list of policies waiting for my review or approval — so that I have a single place to manage my outstanding review actions |  |
| Acceptance criteria | - GET /review-queue renders all workflow_instances where the authenticated user is reviewer, l1_approver, or l2_approver AND state requires their action - Each row shows: policy title, author, submitted date, change magnitude badge, action button - Action button text reflects the user's role: "Review" (reviewer), "Approve (L1)" (l1_approver), "Approve (Final)" (l2_approver) - Empty state shown with message "You're all caught up" - Dashboard attention cards are populated from the same query as the review queue |  |
|  | Depends on | S3-05 |  |

| S3-08 | GitLab webhook receiver | M (3) |
| --- | --- | --- |
| User story | As a system, I want to receive and process GitLab MR events via webhook — so that the application state stays synchronised with GitLab MR status (e.g., comments added directly in GitLab) |  |
| Acceptance criteria | - POST /webhooks/gitlab is registered and protected by X-Gitlab-Token header verification - GITLAB_WEBHOOK_SECRET env var contains the shared secret - Unrecognised event types return 200 (acknowledged) and are discarded - MR comment events sync the comment to the PolicyHub comments table - Webhook handler is idempotent — replaying the same event does not create duplicate records - Processing is delegated to a queue job (not synchronous in the request handler) |  |
|  | Depends on | S1-09 |  |

| S3-09 | Approval chain sidebar component | S (2) |
| --- | --- | --- |
| User story | As a reviewer, I want to see the full approval chain (submitted → reviewer → L1 → L2) with each step's current state on the review screen — so that I understand where the policy is in the workflow and whose action is outstanding |  |
| Acceptance criteria | - Approval chain sidebar shows all steps with: name, role label, status (pending/active/complete/changes-requested) - Active step (current actor's turn) is highlighted per spec - Completed steps show completion date and approver name - Sidebar is a shared React component reusable across the review and policy detail screens |  |
|  | Depends on | S3-07 |  |

| S3-10 | Comments on review screen | M (3) |
| --- | --- | --- |
| User story | As a reviewer, I want to leave comments on a policy under review — so that I can communicate feedback to the author without using a separate channel |  |
| Acceptance criteria | - Comment input appears at the bottom of the approval chain sidebar - POST /api/v1/policies/:id/comments creates a comment record linked to the workflow_instance - Comments are displayed in chronological order with author avatar, name, and timestamp - Author receives an in-app notification and email when a comment is posted on their policy - Comments are scoped to the workflow_instance — a new review cycle shows a clean comment thread |  |
|  | Depends on | S3-07 |  |

Sprint 4  ·  Days 31–45  ·  Diff view, approve & request changes  ·  29 pts

Objective: The full review loop is functional: reviewer reads diff, approves or requests changes, author is notified. Milestone 2 test gate can be run.

10 stories  ·  29 story points

| S4-01 | Unified diff view (Monaco Editor) | L (5) |
| --- | --- | --- |
| User story | As a reviewer, I want to see a clear unified diff of the changes between the previous published version and the submitted draft — so that I can understand exactly what content has changed before making my approval decision |  |
| Acceptance criteria | - Monaco Editor loaded in diff mode on the review screen - Monaco is lazy-loaded (not part of the main bundle) — only loaded on /review/* routes - Diff source: git diff between the policy's branch and main, fetched via GitLab API - Hunks displayed with standard +/− notation and syntax highlighting for Markdown - Diff is read-only in this context (no editing in the review screen) - Long diffs are scrollable within Monaco's viewport without full-page scroll |  |
|  | Depends on | S3-07 |  |

| S4-02 | Side-by-side rendered preview tab | M (3) |
| --- | --- | --- |
| User story | As a reviewer, I want to switch to a side-by-side view showing the before and after versions rendered as formatted HTML — so that I can review the policy in a readable format rather than raw Markdown diff notation |  |
| Acceptance criteria | - "Unified diff" and "Side by side" tabs appear above the diff view - Side-by-side renders the previous version (HTML from policy_versions) on the left and the draft Markdown (rendered via remark) on the right - Changed sections are highlighted with add/remove colours matching the spec - Tab selection is persisted per-session (reviewer preference) - Unified diff is the default view on first load |  |
|  | Depends on | S4-01 |  |

| S4-03 | Approve workflow action | M (3) |
| --- | --- | --- |
| User story | As a reviewer, I want to click "Approve" on a policy and advance it to the next workflow stage — so that the policy progresses through the approval chain without manual coordination |  |
| Acceptance criteria | - POST /api/v1/policies/:id/workflow/approve-l1 transitions state to "l2_pending" (from "review") - Only the assigned l1_approver can call this endpoint for a given workflow_instance - On L1 approval, the L2 approver is notified by email - Approval is recorded in workflow_approvals with approver_id, approved_at, and comment - The GitLab MR is updated with a comment recording the approval event - Attempting to approve a policy not in the correct state for your role returns 422 |  |
|  | Depends on | S3-05 |  |

| S4-04 | Request changes workflow action | M (3) |
| --- | --- | --- |
| User story | As a reviewer, I want to click "Request changes" and send the policy back to the author with feedback — so that the author knows the policy needs revision before it can be approved |  |
| Acceptance criteria | - POST /api/v1/policies/:id/workflow/request-changes requires a non-empty feedback message - Transitions workflow_instance state to "changes_requested" - Policy status badge updates to "Changes requested" (amber) on the dashboard - Author receives an email with the feedback message and a direct link to the editor - Reviewer comments from this cycle remain visible to the author in the editor (inline, highlighted) - The GitLab MR remains open (not closed) when changes are requested |  |
|  | Depends on | S4-03 |  |

| S4-05 | Resubmit workflow action | M (3) |
| --- | --- | --- |
| User story | As a policy author, I want to resubmit my policy after addressing reviewer feedback — so that the review process can continue without creating a new workflow from scratch |  |
| Acceptance criteria | - POST /api/v1/policies/:id/workflow/resubmit is available when status is "changes_requested" - Resubmit triggers a new AI change summary (diff since last submission, not from main) - Previous reviewer comments remain in the thread; a visual divider separates review cycles - Reviewer is re-notified by email with the new change summary - workflow_approvals records the resubmit event for audit purposes |  |
|  | Depends on | S4-04 |  |

| S4-06 | Withdraw workflow action | S (2) |
| --- | --- | --- |
| User story | As a policy author, I want to withdraw a policy from review and return it to draft — so that I can make significant changes that were not captured in the original submission |  |
| Acceptance criteria | - POST /api/v1/policies/:id/workflow/withdraw is available when status is "in_review" or "changes_requested" - Transitions policy back to "draft" status - The GitLab MR is closed (not merged) with a comment: "Withdrawn by author" - Reviewer is notified of the withdrawal by email - A new submission creates a fresh workflow_instance and new GitLab MR |  |
|  | Depends on | S4-04 |  |

| S4-07 | Final approval (L2) workflow action | M (3) |
| --- | --- | --- |
| User story | As a policy approver, I want to give final approval as the L2 approver, completing the review workflow — so that the policy is ready to be published after all required approvals are in place |  |
| Acceptance criteria | - POST /api/v1/policies/:id/workflow/approve-final is available only to the assigned l2_approver when state is "l2_pending" - Transitions workflow_instance state to "approved" - Policy status transitions to "approved" — a distinct state from "published" (publishing is a separate step) - Author is notified that final approval has been granted and publishing is pending - The GitLab MR is ready to merge at this point but is not merged until the publishing pipeline runs |  |
|  | Depends on | S4-03 |  |

| S4-08 | In-app notifications | M (3) |
| --- | --- | --- |
| User story | As a user, I want to see a notification indicator in the sidebar when I have unread notifications — so that I can act on workflow events without relying solely on email |  |
| Acceptance criteria | - Notification dot appears on the sidebar for the user's role-relevant nav items when unread notifications exist - GET /api/v1/notifications returns the 20 most recent notifications for the authenticated user - Notifications are marked read when the user navigates to the relevant page - Notification types: review_requested, changes_requested, policy_approved, comment_added - Notifications older than 30 days are soft-deleted by a daily scheduled job |  |
|  | Depends on | S3-06 |  |

| S4-09 | Review screen routing and access control | S (2) |
| --- | --- | --- |
| User story | As a system, I want the review screen to be accessible only to the assigned reviewer, approvers, and the policy author (read-only) — so that policy content under review is not visible to users outside the approval chain |  |
| Acceptance criteria | - GET /policies/:id/review returns 403 if the user is not: the assigned reviewer, l1_approver, l2_approver, policy owner, or policy:admin - Policy author can view the review screen but cannot approve or request changes - Bouncer policy (WorkflowPolicy) covers all workflow action endpoints - All Bouncer checks covered by unit tests |  |
|  | Depends on | S4-01 |  |

| S4-10 | Milestone 2 test gate preparation | S (2) |
| --- | --- | --- |
| User story | As a developer, I want a seeder and test plan for the M2 usability test focused on diff readability — so that the test gate can be run against a realistic policy under review |  |
| Acceptance criteria | - node ace db:seed --seeder=UsabilityM2Seeder creates: an approved policy (v1), a draft v2 with realistic content changes, assigned reviewer and approver - The test scenario includes: a low-magnitude change (single clause update) and a medium-magnitude change (new section added) - Test plan document lists the 3 tasks participants will complete and the success criteria - All Sprint 3–4 stories have end-to-end test coverage |  |
|  | Depends on | S4-07, S1-08 |  |

M3  Publishing pipeline & version history  ·  Day 70

Goal: Approved policies are published: Markdown is rendered to HTML and PDF, committed to main, and a permanent version snapshot is created. Readers can view version history.

Test gate: Internal walkthrough with the full approval chain. Success criterion: end-to-end from new draft to published policy with version history visible.

Sprint 5  ·  Days 46–55  ·  Publishing pipeline  ·  33 pts

Objective: Approved policies are automatically published: Markdown merged to main, rendered to HTML, PDF generated, version snapshot stored.

10 stories  ·  33 story points

| S5-01 | Publishing pipeline job | L (5) |
| --- | --- | --- |
| User story | As a system, I want an approved policy to be automatically published when the L2 approval is granted — so that the policy becomes available in the reader portal without manual intervention |  |
| Acceptance criteria | - Final approval triggers a PublishPolicyJob dispatched to the queue - Job steps: (1) merge GitLab MR, (2) fetch Markdown from main, (3) render HTML, (4) generate PDF, (5) create policy_versions record, (6) update policy status to "published" - If any step fails, the job retries up to 3 times with exponential backoff then logs to audit_log and alerts policy:admin - Publishing is idempotent — replaying the job with the same version number does not create a duplicate - Job execution time is logged; P95 target is under 30 seconds |  |
|  | Depends on | S4-07 |  |

| S5-02 | Markdown to HTML rendering | L (5) |
| --- | --- | --- |
| User story | As a system, I want policy Markdown to be rendered to HTML with boilerplate injection (metadata, ToC, related policies, version footer) — so that the published HTML is a complete, self-contained document ready for display |  |
| Acceptance criteria | - Markdown is rendered via unified / remark / rehype pipeline - Boilerplate injected from the policy database record: title, category, owner, effective date, review date, audience, version - ToC auto-generated from H2/H3 headings with anchor links - Related policies injected as linked cards from policy_related_policies - Version footer: "Version X.Y — Effective [date] — Owner: [owner]" - Rendered HTML is stored in policy_versions.rendered_html (not re-computed at read time) |  |
|  | Depends on | S5-01 |  |

| S5-03 | PDF generation | M (3) |
| --- | --- | --- |
| User story | As a reader, I want to download a PDF of any published policy version — so that I can read the policy offline or share it with people outside the system |  |
| Acceptance criteria | - Puppeteer renders the policy HTML to PDF with standard A4 page size - PDF includes page headers (policy title, version) and footers (page number, confidentiality notice) - GET /portal/api/policies/:id/pdf responds with the stored PDF (served from Drive storage) - PDF is generated once during publishing and stored — not generated on each download request - PDF is regenerated automatically when a new version is published |  |
|  | Depends on | S5-02 |  |

| S5-04 | Policy version snapshots | M (3) |
| --- | --- | --- |
| User story | As a system, I want an immutable version snapshot to be created in the database each time a policy is published — so that every historical version of a policy is permanently accessible |  |
| Acceptance criteria | - policy_versions record created on each publish with: policy_id, version_number (semver), markdown_content, rendered_html, git_commit_sha, published_by, published_at - version_number auto-increments as major.minor (minor for non-breaking changes, major for structural rewrites — determined by the magnitude score) - policy_versions records are immutable — no UPDATE allowed by the application service layer - GET /api/v1/policies/:id/versions returns all versions for a policy (authoring surface) - GET /portal/api/policies/:id/versions returns all versions (reader surface, role-filtered) |  |
|  | Depends on | S5-02 |  |

| S5-05 | Version history screen | M (3) |
| --- | --- | --- |
| User story | As a reader, I want to see a timeline of all published versions of a policy with change summaries — so that I can understand how the policy has evolved over time |  |
| Acceptance criteria | - GET /portal/policies/:id/history renders the Version History screen from the spec - Timeline shows all policy_versions records in reverse chronological order - Current version has AI change summary shown expanded; older versions show a brief description - Compare dropdowns default to: "from" = previous version, "to" = current - "Show diff" button navigates to /portal/policies/:id/diff?from=vX&to=vY - "View this version" loads the historical rendered_html snapshot |  |
|  | Depends on | S5-04 |  |

| S5-06 | Version diff screen (reader) | M (3) |
| --- | --- | --- |
| User story | As a reader, I want to compare any two published versions of a policy and see what changed — so that I can understand exactly what was updated between any two versions |  |
| Acceptance criteria | - GET /portal/policies/:id/diff?from=v2.2&to=v3.1 renders the Version Diff screen - Diff computed from the markdown_content fields of the two policy_versions records (not re-fetched from GitLab) - Same unified diff / side-by-side tab pattern as the review screen - Stat strip shows: from version, to version, line counts, AI change summary - Version selector dropdowns in topbar allow changing the comparison without navigating back - Read-only — no approval actions or comment input |  |
|  | Depends on | S5-05 |  |

| S5-07 | Minor version publishing (patch updates) | M (3) |
| --- | --- | --- |
| User story | As a policy author, I want to publish a minor update (typo fix, formatting correction) without going through the full approval workflow — so that small corrections can reach readers quickly without blocking the approval queue |  |
| Acceptance criteria | - policy:admin role can trigger a direct publish (POST /api/v1/policies/:id/publish-patch) for policies already in published state - Patch publish does not require a workflow_instance — it goes directly from draft to published - Patch publish increments the patch version number (X.Y.Z) and is clearly marked as "Minor update" in the version history - Patch publishes are fully audit-logged - This endpoint is only available to policy:admin — not to policy:author |  |
|  | Depends on | S5-04 |  |

| S5-08 | Published policy detail view | M (3) |
| --- | --- | --- |
| User story | As a reader, I want to read a published policy with its injected boilerplate, table of contents, and related policies — so that I get a complete, well-structured document without navigating multiple pages |  |
| Acceptance criteria | - GET /portal/policies/:id renders the published policy using the stored rendered_html - Page includes: metadata strip, auto-generated ToC, policy body, related policies, version footer - Right-hand sticky "On this page" nav tracks scroll position and highlights the active section - Review date shown in amber (CSS class) when within 90 days of policy.review_date - "Version history" and "Download PDF" are always accessible from the topbar and right-panel actions |  |
|  | Depends on | S5-02 |  |

| S5-09 | Typesense indexing on publish | M (3) |
| --- | --- | --- |
| User story | As a system, I want newly published policies to be indexed in Typesense immediately after publishing — so that the policy is searchable from the moment it is published |  |
| Acceptance criteria | - IndexPolicyJob is dispatched at the end of the PublishPolicyJob pipeline - Typesense document includes: id, title, category, audience_group_ids, body_text (stripped HTML), version, published_at - audience_group_ids is a multi-value field used for role filtering at query time - Re-publishing a policy updates the existing Typesense document (upsert, not insert) - Index job failure does not fail the publish — it is retried independently |  |
|  | Depends on | S5-01 |  |

| S5-10 | Policy review date reminder job | S (2) |
| --- | --- | --- |
| User story | As a policy owner, I want to receive an email reminder 90 days before my policy's review date — so that I have enough time to initiate a review cycle before the policy becomes overdue |  |
| Acceptance criteria | - A daily scheduled job (node ace queue:work) queries policies where review_date is 90, 60, or 30 days away - Sends a PolicyReviewDueMail to the policy owner and policy:admin users - A policy that already has an active workflow_instance does not trigger a reminder - Reminder emails are logged in audit_logs with type = "review_reminder" |  |
|  | Depends on | S5-01 |  |

M4  Reader portal & search  ·  Day 95

Goal: All staff can browse and search published policies. Access is role-filtered. Typesense full-text search is live. Admin can manage categories and users.

Test gate: Broad staff pilot (all staff with policy library access). Success criterion: users can find the policy they need within 60 seconds without assistance.

Sprint 6  ·  Days 56–70  ·  Reader portal & Typesense search  ·  23 pts

Objective: Staff can browse, search, and read published policies. RBAC filtering is in place. Typesense search is live.

8 stories  ·  23 story points

| S6-01 | Reader portal — category browsing | M (3) |
| --- | --- | --- |
| User story | As a staff member, I want to browse policies by category from the policy library — so that I can quickly find policies relevant to my area without knowing the exact title |  |
| Acceptance criteria | - GET /portal renders the Policy Library screen from the spec - Left sidebar shows only categories that contain at least one policy the user can see - Clicking a category filters the card grid to that category - "All" option shows all accessible policies - Policy cards show: category tag, version, title, description excerpt, last updated - RBAC: policy cards are filtered by the user's audience_group_ids — missing policies return no card (not a locked card) |  |
|  | Depends on | S5-08 |  |

| S6-02 | Typesense full-text search | L (5) |
| --- | --- | --- |
| User story | As a staff member, I want to search across all policy content with typo tolerance and instant results — so that I can find the specific clause or policy I need by keyword without knowing which document it's in |  |
| Acceptance criteria | - Search input in the portal topbar triggers a Typesense query on each keystroke (debounced 200ms) - Query includes filter_by: audience_group_ids:[<user's group ids>] — role filtering at query time - Results show matching excerpts with search terms highlighted - Typo tolerance: "expnes" matches "expense" - Zero-results state shows "No policies match your search" with a suggestion to use the Policy Bot - Search query and result count are logged for the policy gap report |  |
|  | Depends on | S5-09, S6-01 |  |

| S6-03 | Audience group management (admin) | M (3) |
| --- | --- | --- |
| User story | As a policy admin, I want to create and manage audience groups and map them to IdP groups — so that RBAC for the reader portal is managed in PolicyHub without requiring code changes |  |
| Acceptance criteria | - GET /admin/audience-groups renders a list of all audience groups with their IdP group mappings - Admin can create, rename, and delete audience groups - Each audience group maps to one or more IdP group IDs (comma-separated) - Mapping changes take effect on the user's next login (consistent with role mapping behaviour) - Deleting an audience group warns if it is currently assigned to published policies |  |
|  | Depends on | S6-01 |  |

| S6-04 | Category management (admin) | S (2) |
| --- | --- | --- |
| User story | As a policy admin, I want to create and configure policy categories including default L2 approvers — so that the correct approval chains are automatically applied when authors submit policies |  |
| Acceptance criteria | - GET /admin/categories renders a list of categories with their default approver settings - Admin can create, rename, and archive categories - Each category has: name, description, default_l1_approver (optional), default_l2_approver (required) - Archiving a category prevents new policies being created in it but does not affect existing policies |  |
|  | Depends on | S6-01 |  |

| S6-05 | User management (admin) | M (3) |
| --- | --- | --- |
| User story | As a policy admin, I want to view all users, their roles, and IdP group mappings — so that I can diagnose access issues and verify role assignments without accessing the IdP directly |  |
| Acceptance criteria | - GET /admin/users renders a paginated user list with columns: name, email, roles, last login, IdP provider - Admin can manually assign or remove roles from a user (overrides IdP mapping for that user) - Admin can deactivate a user (sessions are invalidated, login is blocked) - IdP group → role mapping table is editable at GET /admin/idp-mappings - All admin actions are logged to audit_logs |  |
|  | Depends on | S6-01 |  |

| S6-06 | Audit log viewer (admin) | M (3) |
| --- | --- | --- |
| User story | As a compliance officer, I want to search and filter the audit log for any user, policy, or action type — so that I can produce an activity report for any policy or user on demand |  |
| Acceptance criteria | - GET /admin/audit-log renders a filterable audit log table - Filters: date range, user, policy, action type - Audit log rows link to the relevant policy or user record - Export to CSV: filtered or full log (up to 12 months) - Audit log is append-only in the UI — no delete or edit controls |  |
|  | Depends on | S1-10 |  |

| S6-07 | 404 for unauthorised portal resources | S (2) |
| --- | --- | --- |
| User story | As a system, I want requests for portal resources the user cannot access to return 404, not 403 — so that users cannot infer the existence of restricted policies by observing error codes |  |
| Acceptance criteria | - GET /portal/policies/:id for a policy the user cannot access returns 404 (not 403) - GET /portal/api/policies/:id for an inaccessible policy returns { "error": "not_found" } with 404 status - Typesense search results never include policies outside the user's audience groups (enforced at query time) - The 404 behaviour is verified by a test asserting that a user with no audience groups receives 404 for all portal policy routes |  |
|  | Depends on | S6-01 |  |

| S6-08 | Rate limiting on portal and API routes | S (2) |
| --- | --- | --- |
| User story | As a system, I want rate limiting applied to portal and API routes to prevent abuse — so that a single user cannot degrade service for all users through excessive requests |  |
| Acceptance criteria | - @adonisjs/limiter applied: 60 requests/min on portal routes, 30 requests/min on API routes, 10 requests/min on auth routes - Rate limit responses return 429 with Retry-After header - Rate limit counters stored in Valkey - Policy bot endpoint has a separate limit: 20 requests/min per user (bot is more expensive) |  |
|  | Depends on | S6-01 |  |

M5  AI features  ·  Day 130

Goal: The policy bot answers questions from published policies with citations. AI change summaries are generated during submission. Authors have an AI writing assistant in the editor.

Test gate: Red team evaluation (internal policy team stress-tests the bot for hallucination and RBAC leakage) + pilot with 10 staff. Success criteria: >85% citation accuracy, zero RBAC leakage incidents.

Sprint 7  ·  Days 71–85  ·  pgvector embeddings & policy bot  ·  31 pts

Objective: The policy bot is live in the reader portal. Questions are answered from published policies with source citations.

7 stories  ·  31 story points

| S7-01 | Database migrations 017–022 (AI tables) | S (2) |
| --- | --- | --- |
| User story | As a developer, I want the pgvector extension and AI-related tables to be created by migrations — so that embedding storage and bot interaction logging are available before the AI pipeline is built |  |
| Acceptance criteria | - CREATE EXTENSION IF NOT EXISTS vector runs as migration 017 - Migrations 018–022 create: policy_chunks, bot_interactions, bot_interaction_sources tables - policy_chunks.embedding column is vector(1536) (Anthropic text-embedding-3-small dimensions) - HNSW index created on policy_chunks.embedding with m=16, ef_construction=64 - All migrations roll back cleanly |  |
|  | Depends on | S1-03 |  |

| S7-02 | Policy chunking and embedding pipeline | L (5) |
| --- | --- | --- |
| User story | As a system, I want published policy content to be split into chunks and embedded into pgvector on publish — so that the bot can retrieve semantically relevant policy content for any question |  |
| Acceptance criteria | - IndexPolicyJob (Sprint 5-09) extended to also run embedding: split Markdown into chunks of ~400 tokens with 50-token overlap - Each chunk stored in policy_chunks with: policy_id, policy_version_id, chunk_index, content, embedding, audience_group_ids - Embeddings generated via Anthropic text-embedding API (model: text-embedding-3-small) - Existing chunks for a policy version are deleted before re-embedding (upsert by policy_version_id) - Embedding failures are retried independently; a partially embedded policy is flagged in audit_logs - node ace ai:embed-all command re-embeds all published policies (for initial backfill) |  |
|  | Depends on | S7-01, S5-09 |  |

| S7-03 | Policy bot RAG endpoint | XL (8) |
| --- | --- | --- |
| User story | As a staff member, I want to ask the policy bot a question and receive an answer grounded in the published policies I am permitted to read — so that I can get a quick, authoritative answer without reading through multiple documents |  |
| Acceptance criteria | - POST /portal/api/bot/ask accepts { question: string } and returns a streaming response - Retrieval: pgvector cosine similarity search on policy_chunks WHERE audience_group_ids && user.audience_group_ids, top 5 chunks - Generation: chunks sent as context to claude-sonnet-4-6 with strict grounding prompt (answer only from provided context) - If no relevant chunks found (similarity < 0.75), return: "I couldn't find a policy that covers this. Try searching the policy library or contact your HR/Finance team." - Response includes source citations: array of { policy_id, policy_title, version, section } - Response is streamed — first tokens appear within 500ms - RBAC verified: audience_group_ids filter applied at retrieval, not post-retrieval |  |
|  | Depends on | S7-02 |  |

| S7-04 | Policy bot popover UI | L (5) |
| --- | --- | --- |
| User story | As a staff member, I want to open the policy bot from a floating button in the portal and have a conversation with it — so that I can ask questions without leaving the page I am reading |  |
| Acceptance criteria | - FAB (floating action button) renders bottom-right on all portal pages matching spec - Clicking FAB opens a popover anchored above the button; popover persists across navigation - Chat input sends to /portal/api/bot/ask; response streams into the message bubble - Source citation pills appear below each bot response - Clicking a citation pill loads the referenced policy in the main panel (portal router navigation) while the popover remains open - Suggested prompt chips appear on first open (3 prompts auto-selected from recent unanswered searches) - "Published policies only" label shown in popover header |  |
|  | Depends on | S7-03 |  |

| S7-05 | Bot interaction logging and gap report | M (3) |
| --- | --- | --- |
| User story | As a policy admin, I want every bot interaction to be logged and questions with no answer to be surfaced as a policy gap report — so that I can identify topics that are not covered by any current policy and prioritise new policy creation |  |
| Acceptance criteria | - Every bot question is logged in bot_interactions with: user_id (hashed), question, answer_given (bool), timestamp - bot_interaction_sources records which policy chunks were cited for each answered question - GET /admin/bot/gap-report returns the 20 most-asked questions that received the "no policy found" response, grouped and ranked by frequency - Gap report is exportable as CSV - Bot interaction logs do not store the full question text for unanswered questions — only a truncated hash for privacy |  |
|  | Depends on | S7-03 |  |

| S7-06 | AI writing assistant in the editor | L (5) |
| --- | --- | --- |
| User story | As a policy author, I want an AI assistant in the editor that can draft sections, check consistency, and summarise my changes — so that I can write better policies faster without switching to a separate tool |  |
| Acceptance criteria | - FAB bottom-right of the editor opens the AI assistant popover (same component as the policy bot, different system prompt) - Suggested prompts: "Draft the scope section", "Check consistency with related policies", "Suggest related policies", "Summarise my changes so far" - Free-text input for custom requests - Responses are inserted into the editor at the cursor position on user confirmation (not automatically) - The AI assistant only has access to: current policy content, category, and titles of related policies — not policy body of other policies - Editor AI calls are rate-limited separately from the bot (10 calls/hour per author) |  |
|  | Depends on | S7-03 |  |

| S7-07 | Red team evaluation tooling | M (3) |
| --- | --- | --- |
| User story | As a developer, I want a set of adversarial test questions for the bot red team evaluation — so that the evaluation can be conducted systematically before the M5 gate is declared passed |  |
| Acceptance criteria | - node ace ai:red-team runs a batch of pre-defined adversarial questions against the bot endpoint - Test categories: RBAC leakage (question referencing a policy the test user cannot see), hallucination (question with no policy answer), prompt injection (questions attempting to override system prompt) - Output: JSON report with question, expected_behaviour, actual_response, pass/fail - A passing red team requires: 0 RBAC leakage incidents, <15% hallucination rate, 0 successful prompt injections - Red team seeder creates two users with different audience groups and overlapping policy sets |  |
|  | Depends on | S7-03 |  |